PDLC

Master Product Brief and Stage Gates

The single artifact that travels with a product from FRAME to LEARN — mapped to the 3-Step PDLC Process (v4.0), Stage Gates, and  the RAPID Role and Decision-Making Framework.

| OUT THIS ARTIFACT | This brief is the standardized artifact for new products, new experiences, or material redesigns. It is not intended for routine compliance, run-the-business updates, or technical maintenance — those follow lighter intake processes. |
| --- | --- |
| STRUCTURE | Six sections, one per PDLC sub-step, grouped into three macro-steps — Define, Create, Deliver. Each section ends with the stage-gate approval checklist for that step — G1 through G5, plus the Loop-to-FRAME gate. Every numbered sub-section (1.1–6.4) states the default RAPID role assignment for that deliverable across the 12 institutional roles (Product VP / AVP / Leader / Manager / Designer, Content Designer, BI Lead, Tech Lead, Agile Coach, Research Lead, Legal, Compliance). Yellow placeholder text [in brackets] is editable. Print or share as PDF for review. |

RAPID Decision Model

Every deliverable in this brief has a named default owner. RAPID assigns one letter, per role, per deliverable — so decisions do not stall waiting on a consensus that was never going to happen.

| Letter | Meaning | Applied in this brief |
| --- | --- | --- |
| R · Recommend | Proposes the direction | The role expected to bring a point of view, not just raise a hand |
| A · Agree | Must formally sign off | Required signature — withholding Agreement blocks the decision |
| P · Perform | Does the hands-on work | Writes the copy, builds the dashboard, ships the code |
| I · Input | Consulted, not binding | Heard and considered — does not have to be satisfied to proceed |
| D · Decide | Makes the final call | Reserved for the Product Leader on every item and every gate in this brief |

Decision rights belong to the Product Leader on every item and every gate below — there are no split deciders. The role-by-role assignment for each of the 31 deliverables is summarized in the “RAPID for this section” table under each numbered heading. The full model — including rationale — is documented in the companion RAPID Decision Matrix deck (PDLC RAPID Matrix and Rationale) and the live playbook at pdlc-playbook.pplx.app.

Project Identity

| Project Name Brief, descriptive name | [Type project name here] |
| --- | --- |
| Owner / Author PM lead and team | [Name, title, team] |
| Date / Version Aligned to the 3-Step PDLC Process (v3.0) and the RAPID Decision Model | [v1.0 — YYYY-MM-DD] |
| Product Group Which of the 9 product groups | [e.g. Digital Sales, Onboarding] |
| Project Type Drives which sections apply | [Select: New Product · New Experience · Material Redesign · Cross-PG Initiative] |
| Target Launch PI Flag any blockers | [Select: PI 26.3 · PI 26.4 · PI 27.1 · Beyond] |
| AI Risk Tier Decisional + Autonomous trigger AI Eval addendum | [None · Assistive · Decisional · Autonomous] |

Sections and stage gates

Each section corresponds to one PDLC sub-step and ends with that step’s gate checklist. Steps group sub-steps into Define, Create, and Deliver — matching the published 3-Step PDLC Process.

| Step | Sub-step | What’s Inside | Exit Gate |
| --- | --- | --- | --- |
| 1. DEFINE | 1a · FRAME | WHO–WHAT–WHY, vision, biz case, measurement, stakeholders + RAPID | G1 · Problem Approved |
| 1. DEFINE | 1b · DISCOVER | Press release, customer quote, FAQ, persona, member journey | G2 · PRFAQ Approved |
| 2. CREATE | 2c · DESIGN | Insights → solution intent → capabilities → boundaries → AI eval | G3 · Build Ready |
| 2. CREATE | 2d · READY | Feature estimation, architecture + design sign-off, story breakdown, handoff to Jira / ADO | G4 · Product Approved |
| 3. DELIVER | 3e · LAUNCH | Legal & compliance review, agile delivery, testing + accessibility, Go/No-Go, deploy + rollback, day-1 enablement | G5 · Ship Ready |
| 3. DELIVER | 3f · LEARN | KPI tracking, drift / data flywheel, post-launch eval, scale / fix / sunset | ↺ Loop to FRAME |

1 · DEFINE Frame the problem, then prove it with research and a launch-ready story.

STEP 1a · FRAME Problem & Business Case · SLA 5–10 days · Exit: G1 Problem Approved

Frame the problem before chasing solutions. WHO is the user, WHAT is the friction, WHY does it matter — plus the business case and measurement plan to back it up.

1.1  WHO — WHAT — WHY

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAID | RAI | RAI | RAI | RAI | RAI | I | RAI | I | I |

The foundational framework for problem definition. Be specific. Avoid solutions.

| WHO Specific user segment experiencing the pain | [Define the user segment — demographics, role, context. Avoid "all members."] |
| --- | --- |
| WHAT The specific friction or unmet need they face | [Describe the observable behavior or pain. Quantify if possible.] |
| WHY Business and user impact of solving this | [Why does this matter? Tie to OKRs and member outcomes.] |
| AI ROLE ☆ Is AI core to the value, or supportive? | [Select: Core (won’t work without AI) · Supportive (AI accelerates a human-led flow) · None. If Core or Supportive, name the model capability — summarization, classification, retrieval, generation, agentic.] |

1.2  Product Vision

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager |  | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAID | RAI |  | RAI | RAI | RAI | RAI | I | RAI | I | I |  |
| NORTH-STAR OUTCOME |  |  |  | [One sentence describing what success looks like for the user] |  |  |  |  |  |  |  |  |
| SCOPE |  |  |  | [What is in / out. Be explicit about boundaries to prevent scope creep] |  |  |  |  |  |  |  |  |
| SUCCESS CRITERIA |  |  |  | [3–5 measurable outcomes. Must be testable post-launch] |  |  |  |  |  |  |  |  |

1.3  Business Case

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager |  | Product Designer | Content Designer | BI Lead | Tech Lead |  | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAID | RAI |  | RAI | RAI | RAIP | RAI |  | I | RAI | I | I |  |
| Element |  |  |  | Description |  |  |  |  | Your Input |  |  |  |  |
| Value Hypothesis |  |  |  | What value will this create? |  |  |  |  | [State the hypothesis] |  |  |  |  |
| ROI Estimate |  |  |  | Revenue, cost savings, member impact |  |  |  |  | [$ amount or % impact, with assumptions] |  |  |  |  |
| Risk Profile |  |  |  | Top 3 risks: regulatory, market, technical, legal |  |  |  |  | [List risks and mitigation approach] |  |  |  |  |
| Total Addressable Market |  |  |  | Quantified user volume or business size |  |  |  |  | [# users / sessions / $ market size, with source] |  |  |  |  |
| Year-1 Financial Impact |  |  |  | Quantified revenue, cost savings, or member impact |  |  |  |  | [$ amount with assumptions] |  |  |  |  |

1.4  Measurement Plan  ☆ NEW

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAID | RAI | RAI | RAI | RAIP | RAI | I | RAI | I | I |

Defined upfront in FRAME, tracked through LEARN. KPIs across four categories. Forces clarity before scope is locked — required to exit G1.

| Element | Description | Your Input |
| --- | --- | --- |
| User KPIs | Member experience, satisfaction, adoption — what the user feels | [Metric · baseline · target · measurement window] |
| Operational KPIs | Process efficiency, throughput, defect rate — how we run | [Metric · baseline · target · measurement window] |
| Business KPIs | Revenue, cost savings, retention — what shows up on the P&L | [Metric · baseline · target · measurement window] |
| Outcome KPIs | Lagging indicators of strategic intent — did we move the OKR? | [Metric · baseline · target · measurement window] |
| Single Success Metric | The one number that defines success for this product | [Metric name + baseline + target + window] |
| Sunset Criteria | When do we stop? Threshold + decision owner + review date | [Threshold + decision owner + review date] |

1.5  Stakeholder Map (RAPID)

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAID | RAI | RAI | RAI | RAI | RAI | I | RAI | I | I |

Name decision rights before Discovery starts. Avoids the HiPPO trap and re-litigation downstream. These are the default institutional roles for this brief — name the individuals for this specific initiative below.

| Role | Default Decision Right (this brief) | Name for This Project |
| --- | --- | --- |
| Product Leader | Decide — sole decider on every item and every gate | [Name] |
| Product VP | Recommend / Agree on 1.1–1.5 and G1; No Role from DISCOVER onward | [Name] |
| Product AVP | Recommend / Agree on 1.1–1.5 and G1; Input from DISCOVER onward | [Name] |
| Product Manager | RAIP — primary owner of PRFAQ, backlog, delivery, and KPI sections | [Name] |
| Product Designer | RAIP on solution intent, capability map, personas, and journey | [Name] |
| Content Designer | RAIP on PRFAQ copy, FAQs, persona voice, day-1 enablement, and legal comms review | [Name] |
| BI Lead | RAIP on measurement plan, KPI tracking, drift / flywheel, and post-launch evaluation | [Name] |
| Tech Lead | RAIP on solution intent, capability map, boundaries, roadmap, backlog, and test / deploy | [Name] |
| Agile Coach | RAIP on sprint delivery, test plan, Go/No-Go, deploy, and day-1 enablement (READY → LAUNCH only) | [Name] |
| Research Lead | Input on every item and every gate — supplies research evidence, method guidance, post-launch interviews | [Name] |
| Legal | RAIP on §5.0 Legal & Compliance Review; Approver on G2, G3, G5. Reviews PRFAQ, external comms, contracts, and AI risk exposure | [Name] |
| Compliance | RAIP on §5.0 Legal & Compliance Review; Approver on G5. Reviews HIPAA, CMS, state regs, WCAG accessibility evidence, and AI governance | [Name] |

Decision rights should not shift from the model above unless a documented exception is approved by the Product Leader. Research Lead is Input on every deliverable and every gate — consulted everywhere but never the decider.

| STAGE GATE G1 · PROBLEM APPROVED Confirms the problem is real, framed, sized — and worth solving. |  |
| --- | --- |
| GATE OWNER (DECIDE) Product Leader | APPROVERS (AGREE) Product VP + Product AVP |
| REQUIRED INPUTS FRAME sections 1.1 – 1.5 complete · Measurement plan drafted | DECISION TYPE Advance to DISCOVER · Conditional · Hold / kill |

RAPID for this gate  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP |  | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI |  | RAI | RAID | RAI | RAI | RAI | RAI | RAI | I | RAI | I | I |  |
| ✓ | APPROVAL CHECKLIST — every box must be checked before this gate advances |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Cross-functional alignment confirmed Problem-only framing — no solutions yet. Product Manager + Tech Lead + Product Designer + BI Lead agree the problem is worth chasing. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | WHO–WHAT–WHY documented and signed off Each line specific and testable. Product VP and Product AVP have agreed in writing. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Business case approved by Finance + sponsor ROI estimate, year-1 financial impact, and risk profile reviewed and approved. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Measurement plan drafted KPIs named across user / operational / business / outcome categories, with BI Lead. Single success metric chosen. Sunset criteria defined. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Stakeholder map and RAPID complete Product Leader confirmed as sole decider. Approvers (Product VP + AVP) and informers identified per the default 12-role RAPID model in 1.5. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | AI Risk Tier set None / Assistive / Decisional / Autonomous selected. Decisional + Autonomous trigger the AI Evaluation addendum (Section 3.5). |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Discovery owner identified and calendar held Named Product Manager owns DISCOVER; calendar blocks held for the 10–15 day SLA. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Strategic anchor to OKR confirmed Initiative is mapped to a single enterprise OKR with quantified expected contribution. |  |  |  |  |  |  |  |  |  |  |  |
| GATE OWNER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  |  | APPROVER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  | OUTCOME ☐ Approved — advance ☐ Conditional — revisit by ____ ☐ Hold / kill |  |  |  |

STEP 1b · DISCOVER Research → PRFAQ → Persona · SLA 10–15 days · Exit: G2 PRFAQ Approved

Validate the problem with research. Write the launch story as if you are launching today. Build the persona and journey before you talk about a solution.

2.1  Press Release (PRFAQ)

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAID | RAPI | RAPI | RAPI | RAPI | RAI | RAI | RAPI | I | I |

Write as if you are launching the product today. If the press release isn’t compelling, the product isn’t worth building.

| Heading Product name + one-sentence description (12 words max) | ["[Company] Launches X for Y…"] |
| --- | --- |
| Subheading Target customer + benefit they receive | ["Designed for [persona] to [benefit]."] |
| Press Release Body 4–5 paragraphs in plain language | [Para 1: Dateline + announcement. Para 2: Why this matters now. Para 3: How it works. Para 4: Why customers care. Para 5: What’s next.] |

2.2  Customer Quote & Getting Started

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager |  | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAID | RAPI |  | RAPI | RAPI | RAPI | RAI | RAI | RAPI | I | I |  |
| Customer Quote Plain language, no corporate-speak |  |  |  | ["…" — [First name], [demographic descriptor], [location]] |  |  |  |  |  |  |  |  |
| Getting Started How easy is it to begin? |  |  |  | [3 steps or fewer for the user] |  |  |  |  |  |  |  |  |
| Call to Action |  |  |  | [Where + how to access — web, app, phone] |  |  |  |  |  |  |  |  |

2.3  External FAQ

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAID | RAPI | RAPI | RAPI | RAPI | RAI | RAI | RAPI | I | I |

5–7 plain-language Q&A: pricing, access, eligibility, support, privacy.

| Question | Answer |
| --- | --- |
| [How do I access this?] | [Plain-language answer] |
| [Is there a cost?] | [Plain-language answer] |
| [Who is eligible?] | [Plain-language answer] |
| [How is my data used?] | [Plain-language answer] |
| [What if I need help?] | [Plain-language answer] |

2.4  Internal FAQ — Required Fields

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAID | RAPI | RAPI | RAPI | RAPI | RAI | RAI | RAPI | I | I |

Standardized so leadership reviews are consistent across initiatives. Required fields must be answered.

| Element | Description | Your Input |
| --- | --- | --- |
| Primary OKR alignment | Select one: Grow Digital Sales · Improve Digital Engagement · Lower Admin Costs | [Select primary OKR; quantify contribution] |
| Funding Status | Select one: Funded — in plan · Partially funded · Unfunded — seeking approval | [Select status; if not funded, name the gap] |
| Build / Buy / Partner | Select one: Build · Buy · Partner · Hybrid | [Select approach; one-line rationale] |
| Regulatory Exposure | Select one: High (CMS / HIPAA / state) · Medium (internal policy) · Low | [Select level; name approving entity] |
| Cross-PG Dependency | Select one: Single PG · 2–3 PGs · 4+ PGs · Enterprise-wide | [Select scope; list dependent PGs] |
| Sunset Trigger Defined? | Select one: Yes (specified) · No (needs to be defined) | [If yes, state metric threshold + decision owner] |

2.5  Persona

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAI | RAI | RAPI | I | I |

Build 1–3 personas per initiative — archetypes, not real individuals.

| Persona Name Memorable nickname | [Name + nickname — e.g. "Cautious Carla"] |
| --- | --- |
| Tagline | [One sentence capturing who they are] |
| Demographics | [Bullet demographics — age, location, income, tenure] |
| % of User Base | [Percentage with source] |
| Primary Channel | [Web, mobile, phone, in-person — channel mix] |
| Goals What they are trying to accomplish | [1. Functional · 2. Emotional · 3. Lifestyle / outcome] |
| Needs | [Functional + emotional needs to achieve their goals] |
| Pain Points | [Top 5 frictions in the current experience — specific, quantified where possible] |
| Tech Comfort | [Low / Med / High; device preferences] |
| Decision Triggers | [Life event, AEP, recommendation, cost change] |
| Quote Plain language | [Verbatim from research interview] |

2.6  Member Journey

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAI | RAI | RAPI | I | I |

Map the customer’s experience across stages — front-stage (what they see/do/feel) and back-stage (systems, teams, handoffs). Default 6-stage model below; customize stage names for your journey.

|  | Awareness | Consideration | Compare & Quote | Decision | Enrollment | Post-Purchase |
| --- | --- | --- | --- | --- | --- | --- |
| Customer Goal | […] | […] | […] | […] | […] | […] |
| Touchpoints | […] | […] | […] | […] | […] | […] |
| Customer Actions | […] | […] | […] | […] | […] | […] |
| Emotions | […] | […] | […] | […] | […] | […] |
| Pain Points | […] | […] | […] | […] | […] | […] |
| Opportunities | […] | […] | […] | […] | […] | […] |
| Back-Stage Systems | […] | […] | […] | […] | […] | […] |
| KPIs to Measure | […] | […] | […] | […] | […] | […] |

| STAGE GATE G2 · PRFAQ APPROVED Confirms research, persona, and launch story add up to a product worth designing. |  |
| --- | --- |
| GATE OWNER (DECIDE) Product Leader | APPROVERS (AGREE) Product Manager + Content Designer + Legal |
| REQUIRED INPUTS DISCOVER sections 2.1 – 2.6 complete · 2 PRFAQ drafts reviewed · 3 personas built · Legal has reviewed external comms | DECISION TYPE Advance to DESIGN · Conditional · Hold / kill |

RAPID for this gate  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP |  | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI |  | RAI | RAID | RAPI | RAPI | RAPI | RAPI | RAI | RAI | RAPI | I | I |  |
| ✓ | APPROVAL CHECKLIST — every box must be checked before this gate advances |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | PRFAQ written, peer-reviewed, sponsor-approved Press release reads like a real launch. Product Leader would publish it. Two review cycles minimum with Content Designer. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | External FAQ covers the 5 must-answer questions Access, cost, eligibility, data use, support — answered in plain language a member would understand. Legal has reviewed member-facing claims. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Internal FAQ required fields complete OKR alignment, funding, build/buy, regulatory exposure, cross-PG dependency, sunset trigger all selected. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | 3 personas built from primary research Each persona grounded in interview data, with Product Designer + Content Designer. Goals, pains, behaviors, channels, quote. No synthetic personas. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Member journey mapped end-to-end All 6 default stages covered (or customized stages documented). Front-stage and back-stage. KPI per stage. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Research evidence catalogued Interview notes, survey results, behavioral data filed in the team’s research repo. Insight statements ready for Section 3.1. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | PRFAQ + persona + journey reviewed by Beacon design partner (if applicable) For initiatives that touch customer-facing UX, the design-system team has reviewed and given written input. |  |  |  |  |  |  |  |  |  |  |  |
| GATE OWNER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  |  | APPROVER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  | OUTCOME ☐ Approved — advance ☐ Conditional — revisit by ____ ☐ Hold / kill |  |  |  |

2 · CREATE Translate research into a scoped, prioritized solution — then break it into sized, sprint-ready work.

STEP 2c · DESIGN Solution → Prototype → Prioritize · SLA 15–20 days · Exit: G3 Build Ready

Translate what we learned into what we’ll build at a conceptual level — before engineering writes a line of code. This is the bridge from research to engineering.

3.1  Insight Statements

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAI | RAI | RAPI | I | I |

“As a [persona], I learned that [observation], because [root cause].” 3–5 statements grounded directly in research.

| ID | Insight |
| --- | --- |
| INS-01 | [As [persona], I learned that … because …] |
| INS-02 | [As [persona], I learned that … because …] |
| INS-03 | [As [persona], I learned that … because …] |
| INS-04 | [As [persona], I learned that … because …] |
| INS-05 | [As [persona], I learned that … because …] |

3.2  Solution Intent

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAI | RAI | RAPI | I | I |

Three-part conceptual solution — plain language, no tech specs.

| Solution Concept | [The big idea, in 1–2 sentences. Plain English. No jargon.] |
| --- | --- |
| Why It Works | [How this addresses the insights above — map directly to INS-01…05] |
| Opportunity | [Volume of users, ROI range, strategic fit — ties back to the business case] |

3.3  Capability Map

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |

List of capabilities the solution must enable — no implementation details. Each will become one or more Features in Jira Align.

| ID | Capability | What it enables | Linked Insight(s) |
| --- | --- | --- | --- |
| CAP-01 | [Capability name] | [What the user can do that they can’t today] | [INS-01, INS-03] |
| CAP-02 | [Capability name] | [What the user can do that they can’t today] | [INS-01, INS-03] |
| CAP-03 | [Capability name] | [What the user can do that they can’t today] | [INS-01, INS-03] |
| CAP-04 | [Capability name] | [What the user can do that they can’t today] | [INS-01, INS-03] |

3.4  Boundaries & Constraints

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager |  | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI |  | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |  |
| MUST HAVE |  |  |  | [Non-negotiable capabilities for MVP] |  |  |  |  |  |  |  |  |
| WON’T HAVE (this round) |  |  |  | [Explicitly excluded from MVP — prevents scope creep] |  |  |  |  |  |  |  |  |
| HARD CONSTRAINTS |  |  |  | [Regulatory deadlines, technical limits, capacity windows] |  |  |  |  |  |  |  |  |
| AI FALL-BACK BEHAVIOR ☆ AI risk tier ≥ Assistive |  |  |  | [Required when AI Risk Tier is Assistive, Decisional, or Autonomous. What the product does when the model fails, is low-confidence, or is unavailable.] |  |  |  |  |  |  |  |  |

3.5  AI Evaluation  ☆  Conditional

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |

Complete this section only when the AI Risk Tier (from 1.1) is Assistive, Decisional, or Autonomous. AI-native products fail in patterns traditional products do not — silent quality degradation, drift, hallucination, and shifting user trust. Sections below force the team to design for those failure modes before shipping.

AI Role Definition

| Use Cases | [List 1–3 specific AI use cases — e.g. "summarize ticket history," "recommend best-fit plan," "auto-draft appeal."] |
| --- | --- |
| Human-in-loop checkpoints | [List each checkpoint with the human role responsible] |
| User transparency | [Disclosure language; consent flow; opt-out + route-to-human] |
| Failure & complaint path | [How users report errors; triage; SLA for human review] |

Model & Data Strategy

| Element | Description | Your Input |
| --- | --- | --- |
| Model Pattern | Single LLM · Orchestrator · Agentic · Classical ML · Hybrid | [Pattern + rationale] |
| Model Provider(s) | Primary + backup. Why this passed procurement and security review. | [Primary + backup model] |
| Data Sources | Each source + access path. PHI/PII handling. Data steward name. | [List sources] |
| Retrieval & Context | Vector DB, embedding model, freshness target | [Vector store + embedding + freshness — or N/A and why] |
| Unit Cost | Expected $ per request and per member per month, plus target gross margin | [$ per req · $ per member/mo · target margin] |
| Privacy & Compliance | HIPAA, CMS, state regs, EU AI Act category | [Frameworks + named approving entity] |

Evaluation & Guardrails

The layer that is easiest to skip and most expensive to add later.

| ID | Metric |  | Target / Threshold | Measurement Method |  |
| --- | --- | --- | --- | --- | --- |
| QM-01 | [e.g. Plan recommendation precision @5] |  | [≥ 0.85, baseline 0.72] | [Weekly eval set of 200 labeled examples] |  |
| QM-02 | [Metric name] |  | [Target] | [How measured] |  |
| QM-03 | [Metric name] |  | [Target] | [How measured] |  |
| QM-04 | [Metric name] |  | [Target] | [How measured] |  |
| QM-05 | [Metric name] |  | [Target] | [How measured] |  |
| INPUT GUARDRAILS |  | [Blocked / sanitized / rate-limited inputs — PII detection, prompt injection defense, off-topic rejection] |  |  |
| OUTPUT GUARDRAILS |  | [Filtered / edited / escalated outputs — hallucination check, toxicity filter, fact-grounding requirement] |  |  |
| HUMAN-IN-LOOP TRIGGERS |  | [Conditions that route to human — low confidence, regulated content, high-dollar impact, complaint] |  |  |
| Drift threshold |  | [e.g. 10% relative drop in QM-01 over a 7-day window triggers review] |  |  |
| Observability stack |  | [Tooling — Datadog, Arize, custom — + dashboard owner] |  |  |
| Kill switch |  | [Conditions to disable + operator who can pull it] |  |  |

Data Flywheel & Learning Loop

| Element | Description | Your Input |
| --- | --- | --- |
| Signal capture | What user interactions become training / eval data | [List interactions captured — accept/reject, edits, downstream conversion, complaint] |
| Feedback design | How users correct the AI | [Explicit feedback UX + implicit signals] |
| Labeling pipeline | How signals become labeled training data | [Auto-labeling rules + human sample + tool + steward] |
| Retraining cadence | How often and on what trigger | [Cadence + drift trigger + budget per cycle] |
| Compounding KPI | The single metric that proves the flywheel works | [Metric that should improve quarter over quarter] |
| Data governance | Consent, retention, deletion, audit | [Consent path + retention window + deletion + audit log] |

| STAGE GATE G3 · BUILD READY Confirms the solution is approved, scoped, and prioritized. Engineering can pick it up. |  |
| --- | --- |
| GATE OWNER (DECIDE) Product Leader | APPROVERS (AGREE) Product Manager + Product Designer + Tech Lead + Legal |
| REQUIRED INPUTS DESIGN sections 3.1 – 3.5 complete · Prototype concept-tested · 4 solution parameters reviewed · Legal reviewed AI risk exposure (if applicable) | DECISION TYPE Advance to READY · Conditional · Hold / kill |

RAPID for this gate  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP |  | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- |  | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |  |
| ✓ | APPROVAL CHECKLIST — every box must be checked before this gate advances |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Insight statements (INS-01…05) grounded in research Each insight cites the persona, observation, and root cause. Not opinion-based. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Solution intent approved by sponsor and engineering Solution concept · why it works · opportunity reviewed and signed off by Product Manager and Tech Lead. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Capability map complete and traced to insights Each CAP-XX maps to one or more INS-XX. No orphan capabilities. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Boundaries explicit — must-have, won’t-have, hard constraints MVP scope locked. Won’t-have list documented to prevent scope creep mid-build. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Prototype concept-tested with users Tested with members representing the persona, with Product Designer. Findings documented. Solution adjusted or accepted with rationale. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Prioritization done (RICE or equivalent) Capabilities ranked by reach × impact × confidence / effort. Top capabilities funded; deferred capabilities logged. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | AI Evaluation addendum complete (if applicable) Required when AI Risk Tier ≥ Assistive. Role, model & data, evaluation & guardrails, and data flywheel all filled in. Legal, Compliance, and Security have reviewed. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Handoff to engineering staged in Jira Align / ADO Capability IDs created in Jira Align. Feature stubs scaffolded. Architecture wiki page started, with Tech Lead. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Measurement plan refined with instrumentation owner KPIs from Section 1.4 mapped to specific telemetry, with BI Lead. Eng owner named for instrumentation work. |  |  |  |  |  |  |  |  |  |  |  |
| GATE OWNER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  |  | APPROVER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  | OUTCOME ☐ Approved — advance ☐ Conditional — revisit by ____ ☐ Hold / kill |  |  |  |

STEP 2d · READY Roadmap → Sizing → Story Breakdown · Continuous backlog grooming · Exit: G4 Product Approved

Where this ends and Jira / ADO begin. Once Build Ready is signed, technical detail lives in Jira Align (Capabilities, Features) and Azure DevOps (Epics, User Stories, Tasks). Feature estimation, architecture and design sign-off, and story breakdown happen here.

4.1  Roadmap Definitions

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader |  | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID |  | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |  |
| Term |  |  | Definition |  |  |  |  |  |  |  |  |  |
| Now |  |  | Currently in active delivery this PI (8–12 weeks). Funded, scoped, in sprint. |  |  |  |  |  |  |  |  |  |
| Next |  |  | Committed for the following PI. Solution Parameters approved; Capabilities defined; not yet in sprint. |  |  |  |  |  |  |  |  |  |
| Later |  |  | Identified opportunities aligned to OKRs, awaiting prioritization. Problem Brief drafted, business case in review. |  |  |  |  |  |  |  |  |  |
| Parking Lot |  |  | Ideas captured but not prioritized. No Problem Brief yet. Re-evaluated each PI Planning. |  |  |  |  |  |  |  |  |  |

4.2  Roadmap Template

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |  |
| Now (PI 26.X) |  |  | Next (PI 26.X+1) |  |  | Later (PI 26.X+2) |  |  | Parking Lot |  |  |
| [Initiative + OKR + status] |  |  | [Initiative + OKR + status] |  |  | [Initiative + OKR + status] |  |  | [Initiative + intake date] |  |  |

4.3  Backlog Hierarchy

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader |  | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID |  | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |  |
| Level |  |  | Definition + System of Record |  |  |  |  |  |  |  |  |  |
| Initiative |  |  | Strategic theme tied to OKR. Approved Problem Brief required. Lives in Jira Align Strategic Themes. |  |  |  |  |  |  |  |  |  |
| Capability |  |  | From the Capability Map (Section 3.3). Cross-team, persists across PIs. Lives in Jira Align Capability. |  |  |  |  |  |  |  |  |  |
| Feature |  |  | Delivers a single capability within one PI. Has acceptance criteria. Lives in Jira Align Feature. |  |  |  |  |  |  |  |  |  |
| Epic |  |  | Group of related stories within a Feature. Lives in ADO Epic. |  |  |  |  |  |  |  |  |  |
| User Story |  |  | As-a / I-want / So-that. Has Given/When/Then acceptance criteria. INVEST. Lives in ADO User Story. |  |  |  |  |  |  |  |  |  |
| Task |  |  | Engineering work to deliver a story (incl. NFR tasks). Lives in ADO Task. |  |  |  |  |  |  |  |  |  |

4.4  Backlog Hygiene Standards

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |

☐  Top 2 sprints’ worth of stories are refined (estimated, AC written, dependencies flagged).

☐  Every Feature traces back to a Capability (CAP-XX) and an Initiative.

☐  Every Story uses INVEST + Given/When/Then format.

☐  NFRs are tracked as Tasks tagged with NFR category (perf, security, a11y, scalability, reliability, compliance, observability).

☐  Backlog reviewed and groomed weekly.

4.5  Handoff to Jira / ADO

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer |  | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI |  | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |  |
| Now (PI 26.X) |  |  |  |  | Next (PI 26.X+1) |  |  |  |  |  |  |  |
| Capability (CAP-XX) |  |  |  |  | → Jira Align Capability |  |  |  |  |  |  |  |
| Solution Concept |  |  |  |  | → Jira Align Feature description |  |  |  |  |  |  |  |
| Functional requirements |  |  |  |  | → ADO User Stories under each Feature — with Given/When/Then acceptance criteria |  |  |  |  |  |  |  |
| Non-functional requirements |  |  |  |  | → ADO Tasks tagged NFR (perf, security, a11y, scalability, compliance, observability) |  |  |  |  |  |  |  |
| Architecture / data model |  |  |  |  | → ADO architecture wiki + Confluence design docs |  |  |  |  |  |  |  |

| STAGE GATE G4 · PRODUCT APPROVED Confirms the roadmap, sizing, and story breakdown are approved — architecture and design have signed off, and engineering can commit stories to a sprint. |  |
| --- | --- |
| GATE OWNER (DECIDE) Product Leader | APPROVERS (AGREE) Product Manager + Tech Lead |
| REQUIRED INPUTS READY sections 4.1 – 4.5 complete · Stories sized and INVEST-checked · Architecture + design sign-off obtained | DECISION TYPE Advance to LAUNCH · Conditional advance (rework backlog) · Hold for resizing |

RAPID for this gate  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP |  | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- |  | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |  |
| ✓ | APPROVAL CHECKLIST — every box must be checked before this gate advances |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Definition of Ready met for every Story Each ADO User Story has Given/When/Then acceptance criteria, is sized, and is free of open dependencies. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | INVEST + acceptance criteria on every story Backlog hygiene audit complete. No stories enter sprint planning without acceptance criteria or test coverage. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Architecture and design sign-off obtained Solution Intent (3.2) reflected in the technical design. Architecture review board and Tech Lead have signed off. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Feature estimation complete T-shirt or story-point sizing done for every Feature in the roadmap window (Now / Next). |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Handoff package staged in Jira Align / ADO Capability IDs created in Jira Align. Feature stubs scaffolded. Architecture wiki page started. |  |  |  |  |  |  |  |  |  |  |  |
| GATE OWNER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  |  | APPROVER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  | OUTCOME ☐ Approved — advance ☐ Conditional — revisit by ____ ☐ Hold / kill |  |  |  |

3 · DELIVER Ship with confidence, then prove the product earned its keep — and feed the loop back to FRAME.

STEP 3e · LAUNCH Legal → Agile → Test → Go/No-Go → Deploy · 2–4 weeks · Exit: G5 Ship Ready

Where the work meets users. Legal & compliance sign-off happens first, then agile delivery in 2-week sprints, rigorous testing including accessibility, a Go/No-Go decision with clear criteria, controlled deploy with rollback ready, and day-1 enablement.

5.0  Legal & Compliance Review  ☆ NEW

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI |

Legal and Compliance run their reviews before Go/No-Go, not after. Evidence filed here becomes part of the G5 packet. Sections 3.5 (AI Eval) and 5.2 (Accessibility) feed directly into this review.

| Element | Description | Your Input |
| --- | --- | --- |
| Regulatory Frameworks in Scope | HIPAA · CMS · State insurance regs · DOJ Title II · EU AI Act · Others | [List frameworks; name the primary approving entity for each] |
| Privacy Assessment | PIA / DPIA status, data flows, PHI/PII handling | [Complete · In progress · N/A. Name Data Steward + attach PIA link.] |
| Accessibility Evidence | WCAG 2.2 AA test results filed with Compliance | [Automated scan · manual audit · assistive-tech test results. Owner: Product Designer.] |
| Contracts & Vendor Review | New vendors, DPAs, model providers, data-sharing agreements | [List new agreements; Procurement + Legal sign-off status] |
| Member-facing Copy Review | Marketing, PRFAQ, in-product copy, FAQs | [Content Designer draft → Legal review → sign-off date] |
| AI Governance (if AI Risk Tier ≥ Assistive) | AI use disclosure, human-in-loop, model cards, drift monitoring | [Model card link · disclosure copy · guardrail evidence · kill switch operator] |
| Complaint & Escalation Path | How members raise concerns; SLA for legal / compliance triage | [Complaint channel · SLA · owner] |
| Documented Risk Acceptances | Any known residual risks accepted by leadership | [Risk · owner · expiration · mitigation plan] |

5.1  Agile Delivery (2-week sprints)

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |

Standard 2-week sprint cadence with planning, daily standup, review, and retro. Capacity tracked, scope locked at sprint start, stretch goals optional. Backlog from READY feeds directly into sprint planning.

5.2  Test Plan + Accessibility

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |

Test plan covers functional, integration, performance, security, and accessibility (WCAG AA). Accessibility review is required before Go/No-Go. Automated test coverage targets defined per project type. Compliance receives WCAG evidence for the §5.0 packet.

5.3  Go / No-Go Criteria

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |

Pre-defined criteria for shipping: all P0 bugs resolved, test pass rate ≥ target, accessibility cleared, observability instrumented, rollback plan rehearsed, §5.0 Legal & Compliance sign-off attached. Product Leader decides Go or No-Go.

5.4  Deploy + Rollback

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |

Phased deploy (canary → 10% → 50% → 100%) with predefined rollback triggers tied to KPIs and error budgets. On-call paged for the first 48 hours. Rollback is non-negotiable if KPIs breach thresholds.

5.5  Day-1 Enablement

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | I | I |

Support, operations, and stakeholders ready before launch: runbooks, FAQs, training, and comms. Day-1 dashboard live with the KPIs from Section 1.4. First retro scheduled within 30 days post-launch.

| STAGE GATE G5 · SHIP READY Confirms the product is built, tested, accessible, legally cleared, and meets acceptance criteria + Definition of Done — ready to ship to production. |  |
| --- | --- |
| GATE OWNER (DECIDE) Product Leader | APPROVERS (AGREE) Product Manager + Content Designer + Tech Lead + Legal + Compliance |
| REQUIRED INPUTS LAUNCH sections 5.0 – 5.5 complete · all P0 bugs resolved · accessibility cleared · rollback rehearsed · §5.0 Legal & Compliance packet filed | DECISION TYPE Ship · Conditional ship (limited release / canary) · Hold for fixes |

RAPID for this gate  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP |  | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| -- |  | -- | RAID | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAI | RAPI | RAPI |  |
| ✓ | APPROVAL CHECKLIST — every box must be checked before this gate advances |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Legal & Compliance packet (§5.0) filed Regulatory frameworks in scope, PIA/DPIA, WCAG evidence, contracts, member-facing copy review, and AI governance artifacts all attached. Legal + Compliance signed. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | All test plans (5.2) executed and passing Functional, integration, performance, security, and accessibility (WCAG AA) tests all green. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Accessibility (WCAG 2.2 AA) verified Required for all member-facing surfaces. DOJ Title II deadline is April 2027. Documented test results filed with Compliance. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Security review complete Threat model, penetration testing for high-risk surfaces, secrets management reviewed. InfoSec sign-off. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Performance NFRs met P95 latency, throughput, error rate within targets defined in Solution Parameters. Load test results documented. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Observability instrumented Metrics, logs, traces emitting. Dashboards live. On-call runbook published. Alert thresholds set per measurement plan. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | AI guardrails live (if applicable) Input + output guardrails enforced. Drift monitoring on. Kill switch documented and tested. Required when AI Risk Tier ≥ Assistive. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Measurement instrumentation live All KPIs from Section 1.4 emitting telemetry, with BI Lead. Baseline captured. Pre-launch dashboard reviewed by sponsor. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Comms and enablement ready Member-facing copy reviewed by Legal + Content Designer. Internal enablement (sales, support, ops) trained and signed off. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Go / No-Go criteria (5.3) reviewed and met Pre-defined criteria for shipping confirmed. Product Leader approves Go decision. |  |  |  |  |  |  |  |  |  |  |  |
| GATE OWNER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  |  | APPROVER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  | OUTCOME ☐ Approved — advance ☐ Conditional — revisit by ____ ☐ Hold / kill |  |  |  |

STEP 3f · LEARN Measure → KPIs → Loop Back · Continuous · Exit: ↺ Loop to FRAME

Where compounding advantage comes from. Activate the measurement plan, watch the KPIs, and feed learnings back into the next FRAME — or sunset gracefully if the product doesn’t earn its keep.

6.1  KPI Tracking — activate the measurement plan

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | -- | -- |

Pull the KPIs defined in Section 1.4 forward. Add baseline, current, and trend. Owner accountable for monthly review.

| Category | KPI | Baseline | Target | Current | Owner |
| --- | --- | --- | --- | --- | --- |
| User | [Metric] | [Value] | [Value] | [Value] | [Name] |
| Operational | [Metric] | [Value] | [Value] | [Value] | [Name] |
| Business | [Metric] | [Value] | [Value] | [Value] | [Name] |
| Outcome | [Metric] | [Value] | [Value] | [Value] | [Name] |

6.2  Drift, Feedback Loop & Data Flywheel

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | -- | -- |

Continuous discipline — track drift, capture corrections, retrain on cadence. Same applies to AI and non-AI products: signals → labels → improvements → retest.

| Element | Description | Your Input |
| --- | --- | --- |
| Drift Watch | What triggers re-evaluation | [e.g. 10% relative drop in single success metric over 7 days] |
| Feedback Capture | How users tell us we’re wrong | [In-product feedback UX + complaint path + sample of session recordings] |
| Insight Reuse | Where learnings are catalogued for future Discovery | [Research repo / Dovetail / shared insight library] |
| Retraining / Iteration cadence | How often and on what trigger | [Monthly · quarterly · event-driven] |
| Compounding KPI | The single metric that proves the loop works | [Improves quarter over quarter] |
| Kill switch / Sunset trigger | Conditions to disable or sunset (from Sec 1.4) | [Threshold + decision owner + review date] |

6.3  Post-Launch Evaluation (90-Day)

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | -- | -- |

90 days after launch. Audit whether the product met intent — yes/no with evidence. The Scale / Fix / Sunset decision itself is made in Section 6.4.

| Did we meet the success metric? | [Yes / No, with evidence — current vs. target. From Section 1.4 single success metric.] |
| --- | --- |
| Did we move the OKR? | [Yes / No, with evidence — quantified contribution. From Section 2.4 primary OKR alignment.] |
| What did we learn about the persona? | [3 insights that change our model of the user. Feeds future Discovery.] |
| What broke that we didn’t predict? | [Defects, complaints, unintended consequences. Required for institutional learning.] |

6.4  Scale / Fix / Sunset

RAPID for this section  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI | RAI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | -- | -- |

Based on the 90-day evaluation in 6.3, decide the product’s fate. This is not optional — every product exits LEARN through one of these three doors, and the Product Leader logs the decision below.

| Decision | Trigger | Owner (Decide / Recommend) | Next Step |
| --- | --- | --- | --- |
| Scale | Success metric met or exceeded; OKR contribution confirmed | Product Leader decides · Product Manager recommends | Roll out to the next Product Group / cohort; carry KPIs forward; open a lightweight FRAME if scope changes. |
| Fix | Success metric partially met; root cause identified and addressable | Product Leader decides · Product Manager + Tech Lead recommend | Scope a fix, re-measure within one PI, and re-run 6.3 before the next Loop-to-FRAME gate. |
| Sunset | Success metric missed with no credible fix path, or Sunset Criteria (1.4) triggered | Product Leader decides · Product Manager + BI Lead recommend | Retire gracefully per the Sunset Criteria in 1.4 — comms, data retention, decommission plan. |

Decision / Decision owner + date: [Scale to next PG · Fix and re-measure · Sunset] — [Name] — [Date]

| STAGE GATE ↺ · LOOP TO FRAME Closes the loop. Confirms the Scale / Fix / Sunset decision (6.4) is made and logged — and what feeds back into the next FRAME. |  |
| --- | --- |
| GATE OWNER (DECIDE) Product Leader | APPROVERS (AGREE) Product Manager |
| REQUIRED INPUTS LEARN sections 6.1 – 6.4 complete · 90-day post-launch eval ran · Scale / Fix / Sunset decision logged · KPIs reported to sponsor | DECISION TYPE Scale (next PG / cohort) · Fix and re-measure · Sunset (graceful retire) · Hold |

RAPID for this gate  →  R Recommend   A Agree   P Perform   I Input   D Decide

| Product VP |  | Product AVP | Product Leader | Product Manager | Product Designer | Content Designer | BI Lead | Tech Lead | Agile Coach | Research Lead | Legal | Compli- ance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAI |  | RAI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | RAPI | -- | -- |  |
| ✓ | APPROVAL CHECKLIST — every box must be checked before this gate advances |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | All KPIs from Section 1.4 reported User, operational, business, and outcome metrics each have baseline · target · current, with BI Lead. No category skipped. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Single success metric verdict documented Met / partial / missed with evidence. If missed, root cause analysis attached. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | OKR contribution quantified Stated contribution vs. actual. If the product didn’t move the OKR, sponsor reviews the funding decision. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Drift monitoring run and reviewed Last 30 days of drift dashboard reviewed, with BI Lead. No silent quality degradation unreported. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Feedback loop produced labeled data Member complaints, edits, and corrections have been catalogued and routed back to next-cycle planning. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Sunset trigger evaluated Sunset criteria from Section 1.4 checked against current state as part of 6.4. If triggered, sunset plan filed. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Insights catalogued for reuse Three insights about persona, problem, or solution are filed in the team research repo with tags for future Discovery. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Scale / Fix / Sunset decision logged (6.4) Product Leader has signed off on Scale / Fix / Sunset and named the next-cycle owner if continuing. |  |  |  |  |  |  |  |  |  |  |  |
| ☐ | Post-launch retro held Team retro completed. Process improvements (PDLC, brief, ceremonies) routed to the PMO. |  |  |  |  |  |  |  |  |  |  |  |
| GATE OWNER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  |  | APPROVER SIGN-OFF Name: ____________________ Date: ____________________ |  |  |  | OUTCOME ☐ Approved — advance ☐ Conditional — revisit by ____ ☐ Hold / kill |  |  |  |

RECONCILIATION CERTIFICATE · v1.1 Cell-by-cell verification of this brief against the canonical PDLC masters.

This certificate documents the September 2, 2026 reconciliation of the Master Product Brief against its canonical source artifacts. No content drift was found; this document was reissued as v1.1 to record the audit.

Scope of reconciliation

| Version reissued | v1.1 — 2026-09-02 |
| --- | --- |
| Previous version | v1.0 — 2026-08-26 |
| Reconciled by | PDLC office |
| Method | Programmatic cell-by-cell diff of all 31 deliverable RAPID rows plus 5 gates + Loop-to-FRAME across three canonical sources. |

Sources compared

| RAPID MASTER | 00-masters/03-RAPID-MASTER.pdf — 37 rows (31 deliverables + 5 gates + Loop-to-FRAME) |
| --- | --- |
| PRODUCT BRIEF MASTER (this document) | 00-masters/04-PRODUCT-BRIEF-MASTER.docx — 31 deliverables in FRAME → LEARN order |
| DEMO SITE MASTER (brief-data.js) | 00-masters/05-DEMO-SITE-MASTER/aug28-pre-rewrite-v3.0/brief-data.js — the data feeding pdlc-playbook.pplx.app |
| PROCESS MASTER (3-Step) | 00-masters/01-PROCESS-MASTER-3Step.pdf — 6 sub-steps, 5 gates, Loop-to-FRAME |
| REFERENCE TABLE | 00-masters/09-PDLC-PROCESS-AND-PRODUCT-BRIEF-REFERENCE-TABLE.pdf — field-level dictionary |

Findings

| Structural alignment | PASS — 3 macro-steps (DEFINE / CREATE / DELIVER), 6 sub-steps (1a FRAME · 1b DISCOVER · 2c DESIGN · 2d READY · 3e LAUNCH · 3f LEARN), 5 exit gates + Loop-to-FRAME, 12 canonical roles. |
| --- | --- |
| Deliverable inventory | PASS — All 31 deliverables present (§1.1–§6.4, including §5.0 Legal & Compliance Review as parallel LAUNCH swimlane). |
| RAPID rows — deliverables | PASS — 31 of 31 rows match brief-data.js and RAPID MASTER cell-for-cell (12 roles × 31 sections = 372 cells verified). |
| RAPID rows — gates | PASS — G1, G2, G3, G4, G5, Loop-to-FRAME approver rows match RAPID MASTER. |
| Product Leader as sole D | PASS — verified on every deliverable and every gate. |
| Gate approver blocks | PASS — Owners, Agree signers, Required Inputs, and Decision Types match the operating model wiki. |
| §3.5 AI Evaluation trigger | PASS — retained; scoped to AI Risk Tier ≥ Assistive. |
| Version alignment statement | PASS — footer aligned to 3-Step PDLC Process v3.0 and RAPID Decision Model. |

Attestation

The Master Product Brief v1.1 is materially identical to v1.0. No RAPID cell, gate approver, deliverable label, or structural element was altered. This reissue exists to record the September 2, 2026 audit and to time-stamp the brief as a current pilot-ready artifact.

The next scheduled reconciliation is triggered by any change to RAPID MASTER, DEMO SITE MASTER, or PROCESS MASTER. If any of those three change, this brief must be re-reconciled in the same pass per the master-artifact sync rule.

Sign-off

| Reissue date | September 2, 2026 |
| --- | --- |
| Reconciled version | v1.1 |
| Next required review | On any change to RAPID / PROCESS / DEMO SITE masters; otherwise no scheduled cadence. |
| Approver (Product Leader) | ________________________ |
| Sign-off date | ________________________ |

End of Master Product Brief v1.1.  Aligned to the 3-Step PDLC Process (v3.0), the RAPID Decision Model, and the live playbook at pdlc-playbook.pplx.app. Reconciled and reissued 9/2/26.